## Sayfa1
Task Name | Start Week | End Week | Duration
Topic Confirmation & Research | 1 | 3 | 2
SDR Setup & Signal Capture Tests | 3 | 4 | 1
Data Collection (Normal Signals and Spoofing Scenarios) | 4 | 5 | 1
Preprocessing & Feature Extraction | 5 | 7 | 2
Spoofing Detection Model Training | 7 | 9 | 2
Visualization Dashboard Development | 9 | 10 | 1
Integration & Testing | 10 | 11 | 1
Report, Final Documentation & Presentation | 11 | 12 | 1

## Sayfa2
Task Name | Start Week | End Week | Duration
Topic Selection & Literature Review | 1 | 3 | 2
Data Acquisition (Open APIs / IMM Data) | 3 | 4 | 1
Data Cleaning & Preprocessing | 4 | 6 | 2
Model Design & Training | 6 | 8 | 2
Model Evaluation & Optimization | 8 | 9 | 1
Visualization Dashboard (Traffic Map) | 9 | 10 | 1
Integration & Testing | 10 | 11 | 1
Report & Presentation | 11 | 12 | 1