TOBB ETU

Economy & Technology University

BIL 495 / YAP 495

Project Management Plan (PMP)

Reference: IEEE 1058 / ISO/IEC 12207

Project Title: A Unified Web-Based Platform for Real-Time NICU Signal Monitoring and AI-Assisted Diagnosis

Institutional Partner: Ertunç Özcan Import & Representation

1. Project Overview

2. Organization and Roles

3. Project Schedule

4. Budget and Resources

5. Risk Management

6. Quality Assurance

7. Appendix

8. References

## 1. Project Overview

Project Goal:
Develop an integrated, secure, and responsive clinical web platform that collects real-time neonatal physiological data from IoMT-enabled devices, analyzes it using AI-based diagnostic models, and presents it through an interactive dashboard for clinicians and hospital staff. The platform is designed to support both single-hospital and multi-hospital deployment scenarios through a centralized cloud-based architecture.

Deliverables:

- Fully functional prototype of NICU Clinical Dashboard.

- AI module for respiratory and cardiac risk detection.

- IoMT middleware supporting MQTT / HL7 / FHIR standards [4].

- Role-based secure access system (admin / clinician / nurse).

- Comprehensive technical documentation and final report.

Key Stakeholders:

- Project Team (Manifetch): İrem Onaran, Merve İçkilli, Şevval Neva Varol, Sacide Sena Filiz

- Academic Supervisor: Çiğdem Avcı (TOBB ETÜ BIL 495 Instructor)

- Institutional Partner: ERTUNÇ ÖZCAN Import & Representation (IoMT device supplier)

- End Users: Clinicians, NICU nurses, hospital IT staff, and healthcare researchers

## 2. Organization and Roles

| Task | Team Member(s) | Description |
| --- | --- | --- |
| Data Collection & Preprocessing | Şevval Neva Varol | Designed the overall layout of the clinical dashboard and prepared simple wireframes for the interface to be used by clinicians and nurses. |
| Backend Development | Merve İçkilli | Developed the server-side logic, handled data communication between the dashboard, AI module, and medical devices. |
| AI Model Development | Sacide Sena Filiz | Built the web interface for data visualization and integrated the main functions of the dashboard. |
| Dashboard Development & Integration | İrem Onaran | Worked on data preprocessing and implemented the first version of the AI-based diagnostic module for signal analysis. |
| System Testing & Optimization | Şevval Neva Varol | Tested each module of the system, identified bugs, and ensured all parts worked together smoothly. |
| Documentation & Presentation | Merve İçkilli | Prepared the project documentation, final report, and presentation materials for academic and industrial review. |

## 3. Project Schedule

The active development phase of the project will start in Spring 2026, focusing on data processing, AI module development, and full system integration.

The schedule below reflects the technical workload and expected progression.

A detailed Gantt Chart showing week-by-week progress will be provided separately (see Appendix A: Gantt Chart).

| Milestone | Description | Timeframe (Weeks) | Deliverable / Output |
| --- | --- | --- | --- |
| M1 – Data Acquisition & Preprocessing | Collect neonatal physiological data (ECG, SpO₂, respiration) from open datasets or synthetic simulators. Perform preprocessing (cleaning, normalization, segmentation). | Week 1–2 | Clean, structured dataset ready for model training and backend integration. |
| M2 – Backend Implementation & Data Handling | Set up backend environment, configure database, and develop secure API endpoints for data transfer and storage. Ensure IoMT communication support (MQTT/HL7). | Week 3–5 | Functional backend capable of receiving and storing real-time or batch NICU data. |
| M3 – AI Model Development | Design AI model architecture, select relevant features, and perform model training and validation for respiratory and cardiac anomaly detection. | Week 6–7 | Validated AI model achieving acceptable accuracy (≥ 85%) on neonatal datasets. |
| M4 – Dashboard Development & Integration | Design and implement UI/UX layout; integrate dashboard frontend with backend and AI module for real-time visualization and alert display. | Week 8–9 | Web dashboard capable of displaying live signal data and AI diagnostic results. |
| M5 – System Testing & Optimization | Perform integration testing, latency measurement, and system performance optimization. Fix bugs and enhance user interface responsiveness. | Week 10–11 | Stable and optimized system with verified data flow from device to dashboard. |
| M6 – Documentation & Presentation | Prepare final technical documentation, project report, and presentation materials for TOBB ETÜ and Ertunç Özcan evaluation. | Week 12 | Completed final report, presentation slides, and demo-ready prototype. |

## 4. Budget and Resources

4.1 Technical Resources:

| Resource Type | Details / Tools | Provided By |
| --- | --- | --- |
| Development Environment | VS Code, GitHub, Docker (for backend integration) | Team |
| Programming Languages | Python (AI module), JavaScript/React (Frontend), Node.js/Flask (Backend) | Team |
| Data Simulation Tools | BioSPPy [6], NeuroKit2 [7] for signal simulation | Team |
| AI/ML Libraries | NumPy, Pandas, Scikit-learn [8], TensorFlow / PyTorch [9] | Open Source |
| Databases | PostgreSQL or MongoDB (for patient signal data) | Team |
| Datasets | PICS-DB & MIMIC-IV Waveform Databases (via PhysioNet) [1], [2] | Open Access |

4.2 Financial Estimation:

This project does not require direct financial expenditure.
All required software tools and datasets are open-source.
Estimated equivalent value of resources:

- Software Licenses (Figma, Docs): Free-tier academic use

- Mentorship & Data Access: Provided by industrial partner (Ertunç Özcan)

Thus, the overall monetary cost is minimal, focusing on human effort and computing resources rather than direct expenses.

## 5. Risk Management

| Risk ID | Risk Description | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| R1 | Data acquisition delays — public neonatal datasets may be large or slow to process, causing delays in AI model training. | Medium | High | Prepare early data samples and synthetic datasets (using BioSPPy/NeuroKit2) to begin preprocessing before full dataset download completes. |
| R2 | Integration issues between backend, AI module, and dashboard (API incompatibility or latency). | Medium | High | Use modular design and early API testing between teams. Establish common data schema and JSON format. |
| R3 | AI model performance below expectations due to noisy or imbalanced neonatal data. | Medium | High | Apply signal denoising and data augmentation. Use multiple datasets (PICS-DB + MIMIC-IV) for better generalization. |
| R4 | Limited real-world data access from hospitals or industry partners (ethical constraints). | High | Medium | Use anonymized or synthetic data in early stages. Request data-sharing approval early from Ertunç Özcan and hospital ethics board. |
| R5 | Time constraints during development (12 weeks) — overlapping modules may cause bottlenecks. | High | Medium | Implement weekly sprint meetings. Prioritize critical modules (data preprocessing → backend → AI). Keep a 1-week buffer for testing. |
| R6 | System reliability and testing limitations — lack of access to real NICU devices for live testing. | Medium | Medium | Simulate IoMT device signals using generated data streams. Validate data flow integrity through unit and integration testing. |
| R7 | Data privacy and legal compliance issues (HIPAA/GDPR) | Low | High | Use anonymized open-source datasets only. Avoid storing personal identifiers. Follow data-handling policy provided by Ertunç Özcan. |
| R8 | Team coordination difficulties due to overlapping roles or workload imbalance. | Medium | Medium | Define clear responsibilities in PMP (Section 2). Use shared GitHub repository and weekly progress reports. |
| R9 | Hardware limitations for AI model training — limited GPU or computing resources. | Medium | Medium | Train models on smaller subsets, optimize model size, or use Google Colab for GPU resources. |
| R10 | Multi-hospital deployment complexity — ensuring proper data isolation and access control across hospitals may increase backend configuration complexity. | Medium | Medium | Use hospital-scoped RBAC and modular backend design. Validate isolation using simulated multi-tenant scenarios during testing. |

## 6. Quality Assurance

This section defines the review, audit, and evaluation processes applied throughout the NICU platform project, ensuring alignment with ISO 9001 Quality Management [3] and TOBB ETÜ 2025 Capstone Guidelines [5].

Quality assurance activities focus on both technical performance and societal compliance, addressing realistic conditions such as economic, environmental, ethical, and legal constraints.

### 6.1 Quality Review and Audit Process

- Weekly Internal Reviews:
 Each development phase (data, backend, AI, dashboard) will be reviewed weekly by the project manager to ensure tasks align with the defined requirements and performance metrics.

- Bi-Weekly Code Audits:
 Code quality and integration between backend, AI, and dashboard modules will be verified using version control history (GitHub commits) and peer review checklists.

- Testing Validation:
 Integration and performance tests will ensure reliability and accuracy of real-time monitoring. Test logs will be documented and reviewed at the end of each sprint.

- External Evaluation:
 Midterm and final audits will be conducted under the supervision of TOBB ETÜ advisors and the industrial partner (Ertunç Özcan R&D).
 Feedback will be recorded and corrective actions applied before final delivery.

### 6.2 Quality Review and Audit Process

| Category | Quality Metric | Verification Method |
| --- | --- | --- |
| Functionality | Real-time data visualization without latency over 1 sec | Performance testing & code profiling |
| AI Accuracy | ≥ 85% accuracy in respiratory/cardiac anomaly detection on test data | Model validation metrics (Precision, Recall, F1-score) |
| Usability | Clinicians can navigate dashboard and interpret signals easily | Usability testing with mock users |
| Reliability | Continuous operation for ≥ 8 hours without system crash | Stress testing with synthetic data streams |
| Security | All data transfers encrypted (HTTPS/TLS) | API security audit |
| Compliance | HIPAA/GDPR adherence and ethical anonymization | Documentation review |
| Maintainability | Modular code structure and clear documentation | Code inspection checklist |

### 6.3 Quality Constraints and Realistic Conditions

| Constraint Type | Evaluation and Impact | Compliance / Mitigation |
| --- | --- | --- |
| Economic / Financial | No direct monetary budget; limited to free-tier and academic resources. | Use open-source software (Python, React, Figma, etc.) and institutional computing resources. |
| Environmental | Minimal environmental footprint due to software-based nature. | Use virtual servers and cloud tools to reduce hardware waste. |
| Socio-Cultural | System aims to improve neonatal care, aligning with humanitarian values. | Ensure user-friendly interface for clinicians; local language support can be added later. |
| Health and Safety | Platform handles health-critical data; reliability is essential. | Implement validation layers before clinical deployment; initial version for research use only. |
| Legal and Ethical | Use of patient data subject to data protection laws (HIPAA/GDPR). | Use only anonymized public datasets; obtain institutional ethics approval before real data use. |
| Technological | Limited computing power for AI model training. | Use lightweight AI architectures; pre-train models offline if needed. |
| Temporal (Time) | 12-week development cycle may limit large-scale testing. | Follow strict milestone schedule and modular integration. |
| Safety & Security | Data integrity and access control must be guaranteed. | Implement authentication and encrypted communication (JWT, HTTPS). |
| Sustainability | Long-term use requires maintainable code and scalability. | Modular design and open API architecture for future expansion. |

### 6.4 Continuous Improvement

### Quality assurance is an iterative process, not a one-time audit.

## After each major milestone, the team will conduct a “Post-Review Meeting” to identify lessons learned.

## All review notes will be stored in the GitHub “/docs/QA_Log.md” file to ensure traceability and accountability.

## Feedback from clinicians and mentors will be incorporated into subsequent updates.

## 7. Appendix

Appendix A – Gantt Chart

The detailed project Gantt Chart is provided as a separate file: manifetch_gannt_chart

This file includes week-by-week progress for all main tasks and milestones:

Phase 1: Data Handling & Preparation (Week 1–2)

Phase 2: Backend Development (Week 3–4)

Phase 3: AI Model Development (Week 5–6)

Phase 4: Dashboard Development (Week 7–8)

Phase 5: System Testing & Optimization (Week 9–10)

Phase 6: Documentation & Presentation (Week 11–12)

## 8. References

[1] PhysioNet, Preterm Infant Cardio-Respiratory Database (PICS-DB), 2020. [Online]. Available: https://physionet.org/content/picsdb/

[2] PhysioNet, MIMIC-IV Waveform Database, 2022. [Online]. Available: https://physionet.org/content/mimic4wdb/

[3] International Organization for Standardization, ISO 9001:2015 – Quality Management Systems – Requirements, Geneva, Switzerland, 2015.

[4] IEEE Standards Association, IEEE Std 1058-2017 – Standard for Project Management Plans, New York, NY, USA, 2017.

[5] TOBB University of Economics and Technology, Bitirme Projeleri Kılavuzu 2025 – Computer Engineering Department, Ankara, Türkiye, 2025. [Online]. Available: https://drive.google.com/drive/folders/1pN9ms4G14hZ-auGCevyi1-p2c9IBl5h2

[6] BioSPPy Developers, BioSPPy: Biosignal Processing in Python, 2023. [Online]. Available: https://biosppy.readthedocs.io

[7] M. Makowski, T. Pham, and D. Martinerie, NeuroKit2: A Python Toolbox for Neurophysiological Signal Processing, 2023. [Online]. Available: https://neurokit2.readthedocs.io

[8] F. Pedregosa et al., Scikit-learn: Machine Learning in Python, Journal of Machine Learning Research, vol. 12, pp. 2825–2830, 2011.

[9] Google Brain Team, TensorFlow: Large-Scale Machine Learning on Heterogeneous Systems, 2016. [Online]. Available: https://www.tensorflow.org