## Gantt Chart Template
| PROJECT TITLE | A Unified Web-Based Platform for Real-Time NICU Signal Monitoring and AI-Assisted Diagnosis |  |  |  |  | COMPANY NAME | [12 empty] | Ertunç Özcan Import & Representation
| PROJECT MANAGER | Şevval Neva Varol |  |  |  |  | DATE | [12 empty] | Spring 2026
[7 empty] | PHASE ONE | [13 empty] | PHASE TWO | [20 empty] | PHASE THREE | [13 empty] | PHASE FOUR | [13 empty] | PHASE FIVE | [13 empty] | PHASE SIX
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
[7 empty] | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S
1 | Data Handling & Preparation
1.1 | Data Collection | Neva | 2026-01-12 | 2026-01-16 | 4 | 14.29% | bar: WEEK 1 M to WEEK 1 R
1.2 | Data Preprocessing | Neva | 2026-01-16 | 2026-01-26 | 10 | 35.71% | bar: WEEK 1 F to WEEK 2 S
1.3 | Unit Testing – Data Handling | Merve | 2026-01-12 | 2026-01-26 | 14 | 50% | bar: WEEK 1 M to WEEK 2 S
2 | Backend Development
2.1 | Backend Setup | Merve | 2026-02-02 | 2026-02-08 | 6 | 14.29% | bar: WEEK 3 M to WEEK 3 S
2.2 | API Development | Merve | 2026-02-08 | 2026-02-18 | 10 | 23.81% | bar: WEEK 3 S to WEEK 5 T
2.3 | Database Configuration | Merve | 2026-02-18 | 2026-02-23 | 5 | 11.9% | bar: WEEK 5 W to WEEK 5 S
2.4 | Unit Testing – Backend | Neva | 2026-02-02 | 2026-02-23 | 21 | 50% | bar: WEEK 3 M to WEEK 5 S
3 | AI Model Development
3.1 | Model Design & Feature Selection | Sena | 2026-02-23 | 2026-02-28 | 5 | 16.67% | bar: WEEK 6 M to WEEK 6 F
3.2 | Model Training & Validation | Sena | 2026-02-28 | 2026-03-09 | 9 | 30% | bar: WEEK 6 S to WEEK 7 S
3.3 | Unit Testing – AI Model | İrem | 2026-02-23 | 2026-03-09 | 16 | 53.33% | bar: WEEK 6 M to WEEK 7 S
4 | Dashboard Development
4.1 | UI/UX Design | İrem | 2026-03-09 | 2026-03-15 | 6 | 21.43% | bar: WEEK 8 M to WEEK 8 S
4.2 | Frontend Integration | İrem | 2026-03-15 | 2026-03-23 | 8 | 28.57% | bar: WEEK 8 S to WEEK 9 S
4.3 | Unit Testing – Dashboard | Sena | 2026-03-09 | 2026-03-23 | 14 | 50% | bar: WEEK 8 M to WEEK 9 S
5 | System Testing & Optimization
5.1 | Integration Testing | Neva | 2026-02-23 | 2026-03-23 | 30 | 39.47% | bar: WEEK 6 M to WEEK 9 S
5.2 | System Test | İrem | 2026-03-23 | 2026-04-13 | 20 | 26.32% | bar: WEEK 10 M to WEEK 12 S
5.3 | Performance Optimization | Neva | 2026-03-30 | 2026-04-06 | 6 | 7.895% | bar: WEEK 11 M to WEEK 11 S
5.4 | UAT / Fixes | Sena | 2026-03-23 | 2026-04-13 | 20 | 26.32% | bar: WEEK 10 M to WEEK 12 S
6 | Documentation & Presentation
6.1 | Report Writing & Presentation Preparation | Merve | 2026-04-06 | 2026-04-13 | 7 | 100% | bar: WEEK 12 M to WEEK 12 S