## Gantt Chart Template
| PROJECT TITLE | A Unified Web-Based Platform for Real-Time NICU Signal Monitoring and AI-Assisted Diagnosis |  |  |  |  | COMPANY NAME | [8 empty] | Ertunç Özcan Import & Representation
| PROJECT MANAGER | Şevval Neva Varol |  |  |  |  | DATE | [8 empty] | Spring 2026
[7 empty] | PHASE ONE | [9 empty] | PHASE TWO | [14 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [9 empty] | PHASE FIVE | [9 empty] | PHASE SIX
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Data Handling & Preparation
1.1 | Data Collection | Neva | 2026-01-12 | 2026-01-19 | 7 | 0%
1.2 | Data Preprocessing | Neva | 2026-01-19 | 2026-01-26 | 7 | 0%
2 | Backend Development
2.1 | Backend Setup | Merve | 2026-02-02 | 2026-02-09 | 7 | 0%
2.2 | API Development | Merve | 2026-02-09 | 2026-02-16 | 7 | 0%
2.3 | Database Configuration | Merve | 2026-02-16 | 2026-02-23 | 7 | 0%
3 | AI Model Development
3.1 | Model Design & Feature Selection | Sena | 2026-02-23 | 2026-03-02 | 9 | 0%
3.2 | Model Training & Validation | Sena | 2026-03-02 | 2026-03-09 | 7 | 0%
4 | Dashboard Development
4.1 | UI/UX Design | İrem | 2026-03-09 | 2026-03-16 | 7 | 0%
4.2 | Frontend Integration | İrem | 2026-03-16 | 2026-03-23 | 7 | 0%
5 | System Testing & Optimization
5.1 | Integration Testing | Neva | 2026-03-23 | 2026-03-30 | 7 | 0%
5.2 | Performance Optimization | Neva | 2026-03-30 | 2026-04-06 | 6 | 0%
6 | Documentation & Presentation
6.1 | Report Writing & Presentation Preparation | Merve | 2026-04-06 | 2026-04-13 | 7 | 0%